## Plan
KSH INFRA Website: Accessibility Audit Fixes - Work Plan
26-10-2026 to 05-11-2026. One developer. Working day: 7 hours 30 minutes, with up to 6 hours of task work. Sunday off; Saturday 31-10-2026 is a working day. Time shown as hh:mm:ss.
# | Change | Estimated time (hh:mm:ss) | Start date | Finish date | Status | Notes
1 | Add a shortcut that lets people who use a keyboard instead of a mouse jump past the top menu straight to the page content | 02:00:00 | 26-10-2026 | 26-10-2026 | Not started
2 | Label the main parts of every page (top menu, page content, footer) so screen-reading software used by blind visitors can find them | 04:00:00 | 26-10-2026 | 26-10-2026 | Not started | Applies to every page. No visible change
3 | Make faded, light-grey text darker so everyone can read it easily, across the whole website | 12:00:00 | 27-10-2026 | 28-10-2026 | Not started | Applies to every page
4 | Tidy up the page headings so visitors using screen-reading software get a clear outline of each page | 04:00:00 | 29-10-2026 | 29-10-2026 | Not started | Applies to every page. No visible change
5 | Confirm with the auditor which part of the page they flagged for "reading order", and correct it | 02:00:00 | 29-10-2026 | 29-10-2026 | Waiting on auditor | The auditor's report does not say which part
6 | Make every button, card and menu usable without a mouse, and clearly highlight the item that is selected | 12:00:00 | 30-10-2026 | 31-10-2026 | Not started | Applies to every page
7 | Add an "Accessibility Statement" page (which standard the website follows and how to report a problem) and link it from the footer | 06:00:00 | 02-11-2026 | 02-11-2026 | Not started | We prepare the draft; KSH approves the wording
8 | Add a Pause button to the moving video at the top of the home page, and remove its unused hidden sound | 04:00:00 | 03-11-2026 | 03-11-2026 | Not started
9 | Show the name and contact details of KSH's Accessibility Officer (Nodal Officer) in the website footer | 01:00:00 | 03-11-2026 | 03-11-2026 | Waiting on KSH | Needs the officer's name, designation, email and phone number
10 | Final testing of all changes on desktop and mobile | 08:00:00 | 03-11-2026 | 05-11-2026 | Not started
11 | Send the updated website to the auditor to test again | 01:00:00 | 05-11-2026 | 05-11-2026 | Not started
12 | Sign-language versions of key videos (an Indian Sign Language interpreter shown in a corner of the video, for deaf visitors) | TBD | TBD | TBD | Waiting on KSH | Likely not needed: the website's only videos are silent background videos (see task 8). To be confirmed with the auditor
| Total estimated time | 56:00:00
Tasks marked "Waiting on KSH" can be completed once KSH sends the details in the Notes column. Sign-language videos are not part of this schedule.

## Day by day
Day-by-day schedule
Up to 6 hours of task work in each 7 hours 30 minutes working day.
Date | Tasks (task # from the Plan tab) | Task time that day
26-10-2026 (Mon) | #1 Add a shortcut that lets people who use a keyboard instead of a mouse jump past the top menu straight to the page content (02:00:00) #2 Label the main parts of every page (top menu, page content, footer) so screen-reading software used by blind visitors can find them (04:00:00) | 06:00:00
27-10-2026 (Tue) | #3 Make faded, light-grey text darker so everyone can read it easily, across the whole website (06:00:00) | 06:00:00
28-10-2026 (Wed) | #3 Make faded, light-grey text darker so everyone can read it easily, across the whole website (06:00:00) | 06:00:00
29-10-2026 (Thu) | #4 Tidy up the page headings so visitors using screen-reading software get a clear outline of each page (04:00:00) #5 Confirm with the auditor which part of the page they flagged for "reading order", and correct it (02:00:00) | 06:00:00
30-10-2026 (Fri) | #6 Make every button, card and menu usable without a mouse, and clearly highlight the item that is selected (06:00:00) | 06:00:00
31-10-2026 (Sat) | #6 Make every button, card and menu usable without a mouse, and clearly highlight the item that is selected (06:00:00) | 06:00:00
02-11-2026 (Mon) | #7 Add an "Accessibility Statement" page (which standard the website follows and how to report a problem) and link it from the footer (06:00:00) | 06:00:00
03-11-2026 (Tue) | #8 Add a Pause button to the moving video at the top of the home page, and remove its unused hidden sound (04:00:00) #9 Show the name and contact details of KSH's Accessibility Officer (Nodal Officer) in the website footer (01:00:00) #10 Final testing of all changes on desktop and mobile (01:00:00) | 06:00:00
04-11-2026 (Wed) | #10 Final testing of all changes on desktop and mobile (06:00:00) | 06:00:00
05-11-2026 (Thu) | #10 Final testing of all changes on desktop and mobile (01:00:00) #11 Send the updated website to the auditor to test again (01:00:00) | 02:00:00